## DWISE Yr1-5 Outputs
|  | Yr1-Yr5 Output Summary - Progress towards total 5yr outputs | [6 empty] | Exceeded/achieved
|  |  |  | Delivery level achieved: |  |  |  |  | On target
Will not achieve
Risk
Project | 5 Year Target | Programme A: Conserving and Restoring | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Total | Remaining | Exceeded by | % achieved | Comments on delivery
A1.171 | 20 | 20 ha of wild flower rich grassland restored and/or managed over 5 years | 0 | 10.69 | 12 | 0 | 0 | 22.69 | 0 | 2.69 | 113.4%
|  | No. of sites improved (not an original target) | 0 | 4 | 4 | 0 | 0 | 8 | 0 | 8 | #DIV/0!
A2.172 | 3.5 | 3.5 ha of grassland enhanced | 0 | 0 | 3.5 | 0 | 0 | 3.5 | 0 | 0 | 100%
| 1 | 1 meadow management and enhancement event held | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 200%
A3.173 | 3 | 3 ha of woodland thinned and native local provenance trees planted or encouraged to regenerate | 2 | 0 | 0 | 0 | 0 | 2 | 0 | -1 | 66.67% | Site area only 2ha so original target not correct
A4.174 | 2 | 2 ha of wild flower rich grassland created | 0 | 2 | 16 | 0 | 0 | 18 | 0 | 16 | 900%
| 10 | 10 volunteers trained in wild flower identification | 9 | 18 | 0 | 0 | 0 | 27 | 0 | 17 | 270%
| 5 | At least 5 visits to the meadow by local school children | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 1 | 120% | Yr5 participant figures included in D1 project
| 6 | 6 walks or events at the meadow | 1 | 10 | 0 | 0 | 0 | 11 | 0 | 5 | 183.3%
A5.175 | 4 | 4 ha of ancient semi-natural woodland restored through rhododendron clearance | 1.1 | 0.8 | 0.96 | 0.54 | 0.7 | 4.1 | 0 | 0.1 | 102.5%
A8.176 | 25 | 25 LWS managed and restored to a favourable or recovering condition. UK BAP Biodiversity habitats enhanced and restored or created | 9 | 11 | 7 | 7 | 7 | 41 | 0 | 16 | 164%
|  | No. of non-designated sites managed and restored to a favourable or recovering condition | 1 | 5 | 10 | 4 | 11 | 31 | 0 | 31 | #DIV/0!
| 13 | 13 LGS restored and returned to a favourable or recovering condition | 0 | 0 | 5 | 1 | 0 | 6 | 0 | -7 | 46.15% | Unable to work on tarmac sites that were originally identified thus no. of sites available reduced
|  | No. of ha of sites restored/maintained/created (not an original target) | 3.74 | 10.07 | 18.37 | 14 | 0 | 46.18 | 0 | 46.18 | #DIV/0!
|  | No. of metres of fencing created (not an original target) | 1278 | 500 | 0 | 0 | 0 | 1778 | 0 | 1778 | #DIV/0!
|  | No. of metres hedge restored (not an original target) | 0 | 627 | 135 | 0 | 0 | 762 | 0 | 762 | #DIV/0!
|  | No. of metres dry stone wall repaired (not an original target) | 0 | 686 | 240 | 381 | 307 | 1614 | 0 | 1614 | #DIV/0!
|  | No. of grants (not an original target) | 0 | 7 | 1 | 2 | 0 | 10 | 0 | 10 | #DIV/0!
A9.177 | 2.3 | 2.3 ha of grassland enhanced benefiting butterflies, pollinators and other insects | 0 | 2.3 | 0 | 0 | 0 | 2.3 | 0 | 0 | 100%
A10.178 | 1 | Enhanced access and interpretation of 1 LGS and enhancement of a Local Wildlife Site supporting priority UK BAP habitat (deciduous woodland) | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
A13.197 | 6 | To restore 6 ha of meadow to increase the species diversity on the reserve. | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 4 | 166.7%
| 1 | To provide 1 clear plan of management for the grassland | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0% | Previous plan under review and updated
A14.179 | 1 | 1 Landscape Management Plan produced. The management of approximately 12ha of historic parkland | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
A15.180 | 1.7 | 1.7 ha of historic woodland conserved | 0 | 0 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 100%
| 250 | Planting of 250 broadleaved trees and shrubs | 50 | 0 | 0 | 0 | 230 | 280 | 0 | 30 | 112%
| 120 | Approximately 120 m of dry stone wall repairs | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 0 | 100%
A16.181 | 1300 | Restoration of 1,300 m of hedgerow by planting of 3,000 hedgerow plants and 120 trees | 0 | 0 | 0 | 0 | 1135 | 1135 | 0 | -165 | 87.31% | Project reinstated but full target will not be achieved due to seasonal activity
| 3000 | Restoration of 1,300 m of hedgerow by planting of 3,000 hedgerow plants and 120 trees | 0 | 0 | 0 | 0 | 5600 | 5600 | 0 | 2600 | 186.7%
| 120 | Restoration of 1,300 m of hedgerow by planting of 3,000 hedgerow plants and 120 trees | 160 | 100 | 50 | 0 | 0 | 310 | 0 | 190 | 258.3%
| 1300 | 1,300 linear meter of timber post and wire fencing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1300 | 0% | Not achieved at this site but output is covered as part of other projects/grants
A17.182 | 2 | Opening up of a minimum of 2 Iconic historical views - Cromford Mill and Willersley Castle and its historic parkland | 2 | 0 | 3 | 3 | 2 | 10 | 0 | 8 | 500%
| 5 | 5 views opened up along the valley - to be identified | 0 | 13 | 6 | 2 | 1 | 22 | 0 | 17 | 440%
A20.183 | 1 | 1 x appraisal report to raise awareness of the site and encourage local participation in its conservation and upkeep for the future. The works would enhance the visual amenity and aid readability and interpretation with 1 panel | 1 | 0 | 1 | 0 | 2 | 4 | 0 | 3 | 400%
| 1 | 1 visible and safe resource for the enjoyment of the local community, school groups and visitors to Duffield | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 200%
| 1 | Develop 1 ‘friends of group’ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0% | NT do not have the resource to manage a group after DWISE thus an established group will not be developed but community engagement events held throughout the project
A21.184 | 1 | 1 appraisal, selection and worked up schedule for restoration of the cottage and interpretation. | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 100% | Tree management, temporary art installion and small scale remedial works
A22.185 |  | Restoration of some of the very few remaining historic features of the quarry industry in hitherto, a nationally important quarrying area, but at relatively modest cost. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | Project not delivered - replaced with A13 & A33
A23.186 | 1 | 1 survey of barns within the Middleton Via Gellia valley area | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 2 | 300% | 61 barns surveyed for 1 report & 2 bat surveys
|  | No. of barns restored within the Middleton Via Gellia valley area (not an original target) | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | #DIV/0!
|  | No. of volunteers trained in surveying skills (not an original target) | 0 | 11 | 0 | 0 | 0 | 11 | 0 | 11 | #DIV/0! | Unique vonlunteers
|  | No. of volunteer support workshops (not an original target) | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | #DIV/0!
A24.187 | 1 | 1 benchmark data report on condition of resource which informs future management and restoration | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100%
|  | No. of volunteers trained in surveying skills (not an original target) | 0 | 0 | 12 | 12 | 3 | 27 | 0 | 27 | #DIV/0! | 16 surveys of 49 walls
|  | No. of volunteer support workshops (not an original target) | 0 | 0 | 0 | 2 | 1 | 3 | 0 | 3 | #DIV/0!
A27.188 | 1 | 1 survey of the former engine house remains and the loading crane. Investigation for additional match funding to undertake conservation work | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 100%
| 1 | 1 conservation / stabilisation of the wheel pit / wheel (addressing its current at risk status) | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 100%
| 1 | Enhanced understanding and appreciation of the working of the equipment in its wider context setting for visitors / schools groups, via 1 interpretation installation | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 4 | 500%
A28.189 | 1 | 1 survey of two weirs - the Rock Weir, Belper and Foundry Weir, Milford | 0 | 0 | 1 | 1 | 13 | 15 | 0 | 14 | 1500% | additional funding allocated to this project
|  | No. of volunteers trained in surveying skills (not an original target) | 0 | 0 | 22 | 8 | 0 | 30 | 0 | 30 | #DIV/0!
|  | No. of volunteer support workshops (not an original target) | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | #DIV/0!
A29.190 | 1 | 1 survey of a historic industrial structure | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 100%
| 1 | 1 ecological survey | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
|  | No. of volunteers trained in surveying skills (not an original target) | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | #DIV/0!
| 1100 | The restoration of a 1100m2 mill pond | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1100 | 0% | The pond site will not be restored as additional funding was not sourced and the land management is being reviewed
A30.191 | 5 | A minimum of 5 heritage features restored | 0 | 6 | 0 | 0 | 2 | 8 | 0 | 3 | 160%
| 4 | 4 small practical on site projects | 0 | 0 | 1 | 1 | 0 | 2 | 0 | -2 | 50% | 5 out of the 6 grants were dry stone walling so counted as heritage features restored
|  | No. of grants (not an original target) | 0 | 3 | 1 | 2 | 0 | 6 | 0 | 6 | #DIV/0!
A31.192 | 1 | 1 van purchased | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
A32.193 | 39000 | £39,000 of in-kind contribution brought into the scheme to cover management & maintenance costs post 2019 | 0 | 0 | 0 | 0 | 39000 | 39000 | 0 | 0 | 100% | partner letters of commitment finailsed in Yr5
A33.204 | 1 | 1 Conservation Management Plan that sets out priorities for a 10 year period that will protect, conserve, restore and enhance the historic and associated landscape. | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
| 1 | The CMP will inform the Green Flag Management Plan and an application for this national award will be submitted in 2015. 1 Green Flag Award. | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
| 120 | Friends of Darley Open Spaces have committed over 120hours of their time to veteran tree and wildflower meadow surveys. | 135 | 0 | 0 | 0 | 0 | 135 | 0 | 15 | 112.5%
| 4 | Implementation of 4 volunteer projects that will increase the number and range of audiences involved with the park. | 0 | 0 | 1 | 3 | 0 | 4 | 0 | 0 | 100%
Project | 5 Year Target | Programme B: Community Participation | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Total | Remaining | Exceeded by | % achieved | Comments on delivery
B1.208 | 1 | 1 new website | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
B2.209 | 1000 | Provide benchmark data on condition of 1,000 heritage assets. | 0 | 28 | 522 | 450 | 0 | 1000 | 0 | 0 | 100%
|  | 1 new website (not an original target) | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | #DIV/0!
| 125 | 125 trained volunteer heritage auditors | 0 | 25 | 64 | 0 | 0 | 89 | 0 | -36 | 71.2% | Agreement reached with HE that quality of volunteers experience is a higher need (unique individuals)
B3.210 | 9 | 9 workshops prior to launch | 1 | 0 | 0 | 0 | 0 | 1 | 0 | -8 | 11.11% | More workshops delivered after launches so target covered by project
| 3 | 3 workshops at launch events | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 100%
| 12 | 12 workshops after launches | 8 | 7 | 4 | 0 | 0 | 19 | 0 | 7 | 158.3%
|  | No. of schools engaged (not an original target) | 4 | 3 | 1 | 0 | 0 | 8 | 0 | 8 | #DIV/0!
|  | No. of community groups (not an original target) | 2 | 3 | 3 | 0 | 0 | 8 | 0 | 8 | #DIV/0!
|  | No. of participants (not an original target) | 134 | 113 | 33 | 0 | 0 | 280 | 0 | 280 | #DIV/0!
B4.211 | 25 | 5 x workshop programmes of 4+1 workshops ( arts+ National Stone Centre visit) - total 25 workshops | 0 | 0 | 1 | 20 | 0 | 21 | 0 | -4 | 84% | Target not met but total number of art workshops delivered meets the overall target
| 1 | 1 taster workshop at each launch event. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0% | Project not started until Yr3.
|  | No. of community groups (not an original target) | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 5 | #DIV/0!
|  | No. of participants (not an original target) | 0 | 0 | 2 | 99 | 0 | 101 | 0 | 101 | #DIV/0!
B5.212 | 15 | Well-dressing & Rangoli - total No of workshops 6 + 9 = 15 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | -12 | 20% | Project completed – overall the number of participants achieved with less workshops delivered
|  | No. of participants (not an original target) | 70 | 0 | 0 | 0 | 0 | 70 | 0 | 70 | #DIV/0!
| 1 | 1 display of well-dressing at launch or other venues to non-DVMWHS audiences with further DerwentWISE information | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
| 11 | Total 11 workshops (5 where group works independently) Stone Mosaic | 0 | 3 | 7 | 0 | 0 | 10 | 0 | -1 | 90.91% | Target not met but total number of art workshops delivered meets the overall target
| 66 | Average of 6 people = 66 participant at the sessions (Stone Mosaic) | 0 | 50 | 144 | 0 | 0 | 194 | 0 | 128 | 293.9%
|  | No. of community groups (not an original target) | 1 | 1 | 2 | 0 | 0 | 4 | 0 | 4 | #DIV/0!
|  | No. of art installations/interpretation | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 2 | #DIV/0!
| 1 | 1 celebratory event at Darley Abbey Day will increase immediate audience numbers and provide opportunity to give further DerwentWISE information | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 100%
B6.213 | 36 | Total number of workshops = 36 at launch and community events and schools | 7 | 8 | 11 | 0 | 0 | 26 | 0 | -10 | 72.22% | Project completed – overall the number of participants achieved with less workshops delivered
| 2 | 2 schools engaged - 1 Derby City & 1 outside DerwentWISE area | 3 | 4 | 0 | 0 | 0 | 7 | 0 | 5 | 350%
|  | No. of community groups (not an original target) | 4 | 5 | 2 | 0 | 0 | 11 | 0 | 11 | #DIV/0!
| 480 | 480 participant target numbers (Taster sessions, launch events and workshops) | 215 | 53 | 212 | 0 | 0 | 480 | 0 | 0 | 100%
B7.214 | 4 | 4 workshops = 2 one day-courses for each art-form (painting & photography) | 0 | 0 | 5 | 6 | 0 | 11 | 0 | 7 | 275%
| 16 | 16 participants | 0 | 0 | 48 | 29 | 0 | 77 | 0 | 61 | 481.2%
|  | No. of community groups (not an original target) | 0 | 0 | 2 | 3 | 0 | 5 | 0 | 5 | #DIV/0!
|  | No. of works displayed: dependant on participants | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | #DIV/0!
B8.215 | 4 | 1 BSL story-teller for 1 day event plus 3 separate walks = 4 activities | 0 | 0 | 4 | 4 | 0 | 8 | 0 | 4 | 200% | Not BSL but with learning and physical needs young people and children
|  | No. of participants (not an original target) | 0 | 48 | 62 | 35 | 0 | 145 | 0 | 145 | #DIV/0!
| 5 | 3 separate ‘toddles’ plus 2 Little Chester walks = 5 activities | 0 | 4 | 0 | 0 | 0 | 4 | 0 | -1 | 80% | Location changed due to access concerns. Total walks number achieved within project
B9.216 |  | No. of workshops | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 8 | #DIV/0!
|  | No. of talks | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 8 | #DIV/0!
| 1 | 1 x Research programme | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100% | UoD research unit will now deliver in Yr5
|  | No. of participants (not an original target) | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 12 | #DIV/0!
B10.217 |  | No. of short films, photographic records and possibly exhibitions of some of the images and films | 0 | 3 | 2 | 1 | 2 | 8 | 0 | 8 | #DIV/0!
|  | No. of schools engaged (not an original target) | 1 | 1 | 2 | 0 | 0 | 4 | 0 | 4 | #DIV/0!
|  | No. of participants (not an original target) | 0 | 44 | 45 | 0 | 0 | 89 | 0 | 89 | #DIV/0!
B11.218 | 48 | Total 40 – 48 workshops. Tasters 10 – 13. Workshops 30 - 35 delivered through different programmes ranging from 2 – 4 workshops with different groups | 0 | 0 | 0 | 1 | 22 | 23 | 0 | -25 | 47.92% | Project revised and no. of workshops reduced as working with less people but more intensively
|  | No. of participants (not an original target) | 0 | 0 | 0 | 28 | 860 | 888 | 0 | 888 | #DIV/0!
B13.219 | 8 | 8 x one-off workshops | 1 | 0 | 0 | 0 | 0 | 1 | 0 | -7 | 12.5% | Project changed and undertaken as a module assignment rather than bespoke workshops
| 4 | 4 x short programmes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4 | 0% | Project changed - will not be completed
| 3 | 3 x residential programmes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0% | Project changed - will not be completed
|  | No. of participants (not an original target) | 543 | 80 | 28 | 0 | 1695 | 2346 | 0 | 2346 | #DIV/0!
|  | No. of exhibitions (not an original target) | 1 | 0 | 1 | 0 | 4 | 6 | 0 | 6 | #DIV/0!
B14.220 | 3 | 3 celebration events sited in south, middle and north of the DerwentWISE area | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 100%
|  | No. of participants (not an original target) | 0 | 0 | 0 | 0 | 4211 | 4211 | 0 | 4211 | #DIV/0!
B15.221 |  | No. of volunteers trained in archaeological skills (no figure used) | 0 | 0 | 15 | 20 | 0 | 35 | 0 | 35 | #DIV/0!
| 2 | 2 surveys carried out in Lea & Bow Wood | 0 | 0 | 4 | 1 | 0 | 5 | 0 | 3 | 250%
| 1 | Creation of 1 management plan for the archaeological remains to sit alongside that of the ecological resource | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 200%
|  | Enhanced HER dataset = No of revised/new entries | 0 | 0 | 61 | 0 | 51 | 112 | 0 | 112 | #DIV/0! | Includes A24 Field Barn entries
B17.222 | 3 | 3 events each with 6 participatory arts workshops (6 workshops not counted as under B3,B6 & B7) | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 100%
|  | No. of participants (not an original target) | 714 | 0 | 0 | 0 | 0 | 714 | 0 | 714 | #DIV/0!
B18.223 | 3 | 3 Fiends Groups established or helped | 0 | 1 | 5 | 2 | 0 | 8 | 0 | 5 | 266.7%
| 5 | 5 Guided walks | 0 | 0 | 3 | 1 | 0 | 4 | 0 | -1 | 80% | Delivered more events and talks to cover target
| 5 | 5 Talks/Events | 0 | 1 | 7 | 17 | 2 | 27 | 0 | 22 | 540%
|  | No. of participants (not an original target) | 0 | 4 | 249 | 1132 | 0 | 1385 | 0 | 1385 | #DIV/0!
|  | No of grants (not an original target) | 0 | 0 | 4 | 4 | 0 | 8 | 0 | 8 | #DIV/0!
B19.224 | 1 | 1 bespoke flight | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
| 1 | 1 report - specialist data processing and analysis of images from bespoke flight | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 200%
|  | Enhanced HER dataset = No of revised/new entries | 0 | 193 | 329 | 0 | 0 | 522 | 0 | 522 | #DIV/0!
Project | 5 Year Target | Programme C: Access & Learning | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Total | Remaining | Exceeded by | % achieved | Comments on delivery
C1.230 | 4 | The improvements of a 8 km canal towpath at Cromford - 4km of actual works | 1.4 | 2.8 | 0.48 | 0 | 0 | 4.68 | 0 | 0.68 | 117% | 8 km have been restored due to physical improvements of 4km of towpath. Includes new paths at Eccelesbourne Staion & Peat Pits Wood
C2.231 | 180 | 180 delivery sessions with schools | 15 | 40 | 29 | 27 | 20 | 131 | 0 | -49 | 72.78%
| 26 | 26 promotional events | 2 | 2 | 2 | 0 | 0 | 6 | 0 | -20 | 23.08% | Not delivered as more celebration events offered
| 10 | 10 celebration events | 0 | 5 | 5 | 7 | 4 | 21 | 0 | 11 | 210%
| 65 | 65 landscape/wildlife features created | 12 | 33 | 20 | 19 | 16 | 100 | 0 | 35 | 153.8%
|  | No. of schools engaged (not an original target) | 5 | 5 | 4 | 5 | 4 | 23 | 0 | 23 | #DIV/0!
|  | No. of teachers trained (not an original target) | 15 | 35 | 0 | 0 | 0 | 50 | 0 | 50 | #DIV/0!
| 6340 | 6,340 school children engaged | 300 | 1230 | 972 | 2199 | 1027 | 5728 | 0 | -612 | 90.35% | Includes Young adults from YMCA 18-30 year olds
C3.232 | 20 | 20 residential visits | 1 | 5 | 6 | 4 | 3 | 19 | 0 | -1 | 95%
| 5 | 5 Family/carers gathering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5 | 0% | Activities covered by Wildlife Guardians project
| 240 | 240 school children/participants | 60 | 198 | 145 | 132 | 177 | 712 | 0 | 472 | 296.7% | Yr5 included from A4 project
|  | No. of schools engaged (not an original target) | 2 | 4 | 2 | 3 | 1 | 12 | 0 | 12 | #DIV/0!
|  | No. of community groups (not an original target) | 0 | 1 | 3 | 2 | 2 | 8 | 0 | 8 | #DIV/0!
| 1 | 1 ‘heritage spotters trail’ for schools travelling by train along the Derwent Valley | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100%
C4.233 | 24 | 24 workshops - collecting narrative historical accounts of the development of the local sandstone quarrying industries | 4 | 12 | 8 | 8 | 0 | 32 | 0 | 8 | 133.3%
| 240 | 240 participants | 40 | 99 | 58 | 42 | 0 | 239 | 0 | -1 | 99.58%
|  | No. of community groups (not an original target) | 0 | 4 | 1 | 0 | 0 | 5 | 0 | 5 | #DIV/0!
| 1 | 1 published report | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 200%
C5.234 | 1 | 1 full condition survey of the Derwent Valley Heritage Way Trail | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100%
C7.235 | 100000 | Enable 100,000 visitors annually to engage with regional heritage | 0 | 129238 | 126772 | 0 | 0 | 256010 | 0 | 156010 | 256%
|  | 1 decked viewing platform (not an original target) | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | #DIV/0!
|  | 2 interpretation panels (not an original target) | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | #DIV/0!
C8.236 | 1 | 1 leaflet in print & web format | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100%
|  | No of volunteers trained in access audit skills (not an original target) | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 25 | #DIV/0!
C9.237 | 1 | 1 published report | 0 | 0 | 0 | 2 | 1 | 3 | 0 | 2 | 300%
C12.238 | 1 | 1 smart phone app | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 100%
|  | 1 musical composition of 45 minutes long (not an original target) | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | #DIV/0!
|  | No. of participants (not an original target) | 0 | 0 | 30 | 0 | 45 | 75 | 0 | 75 | #DIV/0! | Target covered under B14 final celebration statistics
C13.239 | 8 | 8 interpretation panels | 2 | 0 | 0 | 13 | 3 | 18 | 0 | 10 | 225%
|  | No. of pages on website (no figure used) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
C17.240 | 1 | 1 new guide book for the Derwent Valley Heritage Way Trail produced | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100%
C19.241 | 4 | A minimum of 4 grant awards depending on the value of each grant awarded | 0 | 3 | 3 | 6 | 0 | 12 | 0 | 8 | 300%
|  | No. of interpretation panels (not an original target) | 0 | 5 | 0 | 8 | 13 | 26 | 0 | 26 | #DIV/0!
|  | No. of sites improved (not an original target) | 0 | 1 | 1 | 1 | 1 | 4 | 0 | 4 | #DIV/0!
Project | 5 Year Target | Programme D: Training | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Total | Remaining | Exceeded by | % achieved | Comments on delivery
D1.251 | 16 | 16 participants trained as Level 3 Forest School Practitioners | 15 | 0 | 1 | 0 | 0 | 16 | 0 | 0 | 100%
| 96 | Total 96 - The 16 participants lead a minimum of 6 sessions (of between 2 and 6 hours duration) in an outdoor and woodland environment with a client group | 6 | 118 | 6 | 0 | 0 | 130 | 0 | 34 | 135.4%
|  | No. of schools engaged (not an original target) | 12 | 11 | 1 | 0 | 0 | 24 | 0 | 24 | #DIV/0!
| 240 | 100 to 240 young people each going on 6 sessions | 413 | 520 | 0 | 0 | 24 | 957 | 0 | 717 | 398.8% | Yr5 included from A4 project
D2.252 |  | No. of publicity materials (not an original target) | 2 | 10 | 8 | 12 | 0 | 32 | 0 | 32 | #DIV/0!
| 22 | 22 subsidised places | 9 | 28 | 18 | 12 | 0 | 67 | 0 | 45 | 304.5% | Yr1 - 22 (nothing in for Yrs2-5)
| 10 | 10 accredited courses | 2 | 7 | 6 | 9 | 1 | 25 | 0 | 15 | 250% | 136 courses (Yr1 -32 & Yrs2-5 104) in total excluding family learning - minus 10 accredited & 15 events
| 50 | 50 non-accredited courses | 8 | 32 | 21 | 10 | 0 | 71 | 0 | 21 | 142%
| 16 | 16 family learning sessions | 0 | 1 | 7 | 4 | 0 | 12 | 0 | -4 | 75% | Additional activities delivered by DACES. Yr1 - 2 & Yrs2-5 14
| 15 | 15 events attended | 3 | 7 | 7 | 5 | 10 | 32 | 0 | 17 | 213.3% | see above accredited/non-accredited notes
| 927 | 927 participants | 306 | 464 | 555 | 935 | 855 | 3115 | 0 | 2188 | 336% | Yr1 192 & Yrs2-5 735
| 500 | 500 learning hours | 104 | 312 | 275 | 321 | 85 | 1097 | 0 | 597 | 219.4% | 100 average target taken for each year as not provided for all years (details from Business plans & tenders)
|  | No. of bespoke courses/workshops (not an original target) | 0 | 4 | 4 | 9 | 2 | 19 | 0 | 19 | #DIV/0!
D3.253 | 24 | 24 practical training sessions | 2 | 10 | 3 | 6 | 7 | 28 | 0 | 4 | 116.7%
| 390 | 390 participants for practical training (only Yr1 figures provided) | 44 | 111 | 66 | 111 | 78 | 410 | 0 | 20 | 105.1%
| 43 | 43 walks, talks and family events | 5 | 17 | 17 | 17 | 14 | 70 | 0 | 27 | 162.8%
| 860 | 860 participants walks, talks and family events | 112 | 1095 | 1138 | 1645 | 579 | 4569 | 0 | 3709 | 531.3%
|  | No. of records created for Local Biological Record Centre (figure not used) | 120 | 240 | 300 | 440 | 440 | 1540 | 0 | 1540 | #DIV/0!
| 20 | 20 youth and family rangers sessions for Wildlife Rangers | 3 | 3 | 4 | 6 | 8 | 24 | 0 | 4 | 120%
| 5 | 5 family learning sessions WATCH (only Yr1 & Yr 2) for Wildlife Rangers | 1 | 2 | 1 | 0 | 0 | 4 | 0 | -1 | 80% | Not achieved as delivery through Wildlife Ranger activities
|  | No. of community groups (not an original target) | 4 | 5 | 9 | 3 | 4 | 25 | 0 | 25 | #DIV/0!
|  | 300 youth and family rangers participants for Wildlife Rangers | 62 | 105 | 67 | 77 | 55 | 366 | 0 | 366 | #DIV/0!
D7.254 |  | No. of training sessions delivered (not an original target) | 0 | 3 | 5 | 0 | 0 | 8 | 0 | 8 | #DIV/0!
|  | No. of participants (not an original target) | 0 | 54 | 25 | 0 | 0 | 79 | 0 | 79 | #DIV/0!
Project | 5 Year Target | Programme E: Additional Scheme Office outputs to be captured | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Total | Remaining | Exceeded by | % achieved | Comments on delivery
258 & 259 |  | No of schools | 0 | 0 | 3 | 2 | 11 | 16 | 0 | 16 | #DIV/0!
|  | No of publicity materials (articles, posters, leaflets, e-news) | 8 | 31 | 21 | 10 | 11 | 81 | 0 | 81 | #DIV/0!
|  | No of twitter followers | 0 | 250 | 149 | 93 | 104 | 596 | 0 | 596 | #DIV/0!
|  | No of Facebook likes | 0 | 114 | 261 | 59 | 69 | 503 | 0 | 503 | #DIV/0! | Figures include Aqueduct Cottage Facebook account
|  | No of community groups worked with | 23 | 17 | 36 | 31 | 32 | 139 | 0 | 139 | #DIV/0!
|  | No of tenders/invitation to quotes/call outs | 9 | 7 | 6 | 2 | 0 | 24 | 0 | 24 | #DIV/0!
|  | No of business plans | 1 | 1 | 1 | 1 | 0 | 4 | 0 | 4 | #DIV/0!
|  | No of press releases | 2 | 1 | 9 | 4 | 6 | 22 | 0 | 22 | #DIV/0!
|  | No of landowners engaged | 18 | 18 | 10 | 13 | 3 | 62 | 0 | 62 | #DIV/0! | 62 unique landowners/land managers
|  | No of site visits (including grants) | 19 | 26 | 12 | 20 | 8 | 85 | 0 | 85 | #DIV/0!
|  | No of scheme office events attended (including presentations) | 6 | 22 | 23 | 16 | 11 | 78 | 0 | 78 | #DIV/0!
|  | No of people engaged at scheme office events (including presentations) | 172 | 639 | 1038 | 770 | 409 | 3028 | 0 | 3028 | #DIV/0!
|  | Total no grassland/meadow | 10 | 14.99 | 31.5 | 0 | 0 | 56.49
|  | Total no woodland | 3.1 | 0.8 | 2.66 | 0.54 | 0.7 | 7.8
|  | Total no general (A8) | 3.74 | 10.07 | 18.37 | 14 | 0 | 46.18
|  | Total Ha's improved | 16.84 | 25.86 | 52.53 | 14.54 | 0.7 | 110.47
|  | Total no of people worked with, trained, volunteers | 3242 | 5014 | 5053 | 7324 | 10021 | 30654
|  | Total no engaged social media | 0 | 364 | 410 | 152 | 173 | 1099
|  | Total people engaged | 3242 | 5378 | 5463 | 7476 | 10194 | 31753
|  | Total no of schools engaged (not individual) | 27 | 28 | 13 | 10 | 16 | 94 |  |  |  | 47 Individual schools engaged
|  | Total no of community group engagements (not individual) | 48 | 46 | 72 | 53 | 47 | 266 |  |  |  | 112 individual groups engaged
|  | Total no of grants | 0 | 13 | 9 | 14 | 0 | 36
|  | Total no of reports | 4 | 1 | 3 | 3 | 20 | 31 |  |  |  | include surveys where a report is produced & Mgt & Action plans
|  | Total no of people trained in heritage surveying | 0 | 36 | 125 | 65 | 3 | 229
|  | Lnadonwers engaged (indivdual site visits) | 18 | 18 | 10 | 13 | 3 | 62
Note on I107: Tania Pells: 7 films John smedleys (B13) Duffiled Castle (B13) Wildlife Rangers (D3) Markeaton school (C2) Umbrella Enthusiam for YP (B9) Musical Composition (C12) 1 X Photgraphic exhibition Long Row school 28.03.19
Note on C141: Tania Pells: 1,300 at promotional events 5,040 at delivery sessions 03.07.17
Note on C204: Tania Pells: not including project specific events 03.07.17
Note on C205: Tania Pells: not including project specific events 03.07.17